**Schedule Document:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Task/Activities** | **Duration (Days)** | **Dependencies** | **Expected Start (Day)** | **Expected End (Day)** |
| Reqs | 5 | None | 0 | 5 |
| WBS | 2 | Reqs | 5 | 7 |
| Arch | 3 | Reqs | 5 | 8 |
| DB Schema | 3 | Arch | 8 | 11 |
| Repo | 2 | Reqs | 5 | 7 |
| Auth | 8 | DB Schema, Repo | 11 | 19 |
| Profiles | 5 | Auth | 19 | 24 |
| Signals API | 15 | Auth | 19 | 34 |
| Targets | 8 | Signals API | 34 | 42 |
| Reactions | 5 | Signals API | 34 | 39 |
| Watchlist | 4 | Signals API | 34 | 38 |
| Plans | 5 | Auth | 19 | 24 |
| Checkout | 10 | Plans | 24 | 34 |
| Market | 10 | DB Schema, Repo | 11 | 21 |
| Notify | 8 | Signals API, Checkout | 34 | 42 |
| Leaderboard | 6 | Targets | 42 | 48 |
| Unit Tests | 12 | Auth, Signals API, Market, Notify, Leaderboard | 48 | 60 |
| Integration | 8 | Unit Tests | 60 | 68 |
| Security | 7 | Auth, Signals API, Checkout | 24 | 31 |
| Staging | 3 | Integration | 68 | 71 |
| Prod | 2 | Staging | 71 | 73 |
| Decom | 2 | Prod | 73 | 75 |